INDIPIPS

India's Premier Proprietary Trading Platform

DETAILED DEVELOPMENT TIMELINE & PROJECT PLAN

| Document Info | Details |
| --- | --- |
| Project Name | Indipips — Indian Prop Trading Platform |
| Document Type | Development Timeline & Sprint Plan |
| Total Duration | 60 Days (8 Weeks + Buffer) |
| Build Strategy | Parallel development — all tracks run simultaneously |
| Target Launch | Production MVP — 1,000 Traders Capacity |
| Version | v1.0 — March 2026 |

# 1. Project Overview & Strategy

## 1.1 Build Philosophy

The Indipips development follows a parallel-track strategy where all major components are built simultaneously by different team members or by one developer context-switching efficiently. Rather than a sequential waterfall approach, this timeline is designed so that the database, backend, frontend, integrations, and admin panel all progress in lockstep — reducing total build time from 4-5 months to 60 days.

## 1.2 Development Tracks

| Track | Components | Start Week | End Week |
| --- | --- | --- | --- |
| Track A | Database Design + Backend API + Authentication | Week 1 | Week 4 |
| Track B | Frontend (Landing Page + Trader Dashboard) | Week 1 | Week 5 |
| Track C | Risk Engine + Real-Time System (Socket.io) | Week 3 | Week 6 |
| Track D | Integrations (Razorpay, Aadhaar, Broker API) | Week 3 | Week 7 |
| Track E | Admin Panel + Payout + Notifications | Week 4 | Week 7 |
| Track F | QA, Security Audit, Deployment, Launch | Week 7 | Week 8 |

## 1.3 Team Role Assumptions

This timeline is designed for a solo developer (you) with AI assistance (Claude), but is equally applicable to a small team. Roles are defined for clarity:

| Role | Responsibility |
| --- | --- |
| Full-Stack Developer (You) | All code — Frontend React, Backend Node.js, Database, Integrations |
| AI Pair Programmer (Claude) | Code generation, debugging, architecture decisions, documentation |
| Business Owner (You) | Feature decisions, testing, content, legal, investor communication |
| Tester (You + Beta Users) | Manual QA, edge case testing, user acceptance testing |

## 1.4 High-Level 60-Day Roadmap

| Week | Primary Focus | Key Deliverable | Status |
| --- | --- | --- | --- |
| Week 1 | Foundation Setup | Project scaffold, DB schema, Auth backend, Landing page skeleton | Planned |
| Week 2 | Core Backend + Landing | All Auth APIs live, Landing page complete, Challenge plans API | Planned |
| Week 3 | Dashboard + Payment | Trader dashboard UI, Razorpay integration, Challenge purchase flow | Planned |
| Week 4 | Risk Engine + Broker API | Real-time P&L, Drawdown monitoring, Upstox API sync | Planned |
| Week 5 | Admin Panel + KYC | Admin dashboard, Aadhaar KYC, Payout request system | Planned |
| Week 6 | Referral + Certs + Notifs | Referral program, Digital certificates, Email + SMS system | Planned |
| Week 7 | Integration + Polish | End-to-end testing, Bug fixes, Mobile responsiveness | Planned |
| Week 8 | Security + Deployment | Security audit, Production deploy, Beta launch | Planned |

# 2. Week-by-Week Detailed Plan

| W1 | WEEK 1 — Foundation & Project Setup | Days 1–7 |
| --- | --- | --- |

### Objectives

- Set up complete project structure — frontend, backend, database

- Design and implement full database schema

- Build authentication system (register, login, JWT)

- Create landing page skeleton with all sections

- Configure development environment and CI/CD pipeline

| Task / Deliverable | Owner | Days | Priority | Dependency / Notes |
| --- | --- | --- | --- | --- |
| Initialize Git repository + monorepo structure | Developer | 0.5 | Critical | Must be first step |
| Setup React + Vite + Tailwind CSS frontend | Developer | 0.5 | Critical | Base for all UI |
| Setup Node.js + Express backend with folder structure | Developer | 0.5 | Critical | Base for all APIs |
| Setup PostgreSQL database + Prisma ORM | Developer | 1 | Critical | Before any model creation |
| Write complete database schema (all 9 tables) | Developer | 1 | Critical | Refer SRS Section 8 |
| Run Prisma migrations — create all tables | Developer | 0.5 | Critical | After schema finalized |
| Implement User Registration API with OTP | Developer | 1 | Critical | MSG91 integration needed |
| Implement Login API with JWT token generation | Developer | 1 | Critical | bcrypt password hashing |
| Implement Email verification flow | Developer | 0.5 | High | SendGrid integration |
| Build Landing Page — Hero section + Navbar | Developer | 1 | High | Mobile responsive |
| Build Landing Page — How It Works + Features sections | Developer | 1 | High | Static content |
| Setup Vercel deployment for frontend | Developer | 0.5 | Medium | Auto-deploy on push |
| Setup Railway deployment for backend + DB | Developer | 0.5 | Medium | Production environment |
| Configure environment variables and .env files | Developer | 0.5 | Critical | Never commit secrets |
| Week 1 review — test all auth APIs with Postman | Developer | 0.5 | Critical | Document all endpoints |

Week 1 Milestone: Working authentication system + deployed skeleton app accessible at indipips.com

| W2 | WEEK 2 — Backend APIs + Landing Page Completion | Days 8–14 |
| --- | --- | --- |

### Objectives

- Complete all backend APIs for challenges, plans, and user management

- Finish landing page — all sections including pricing, testimonials, FAQ

- Implement password reset and 2FA flows

- Build challenge plans management system

- Begin Razorpay integration setup

| Task / Deliverable | Owner | Days | Priority | Dependency / Notes |
| --- | --- | --- | --- | --- |
| Build Challenge Plans API (GET all plans, GET plan by ID) | Developer | 0.5 | Critical | Static data initially |
| Build Challenge Purchase API (create challenge on payment) | Developer | 1 | Critical | Depends on Razorpay |
| Build User Profile API (GET, UPDATE profile) | Developer | 0.5 | High | Auth required |
| Build Password Reset API (OTP-based) | Developer | 0.5 | High | MSG91 + SendGrid |
| Implement 2FA for Admin login (mandatory) | Developer | 0.5 | Critical | Admin security requirement |
| Implement refresh token rotation mechanism | Developer | 0.5 | High | JWT security |
| Build Challenges List API (trader's own challenges) | Developer | 0.5 | Critical | Paginated response |
| Build Challenge Detail API (with real-time stats) | Developer | 1 | Critical | Core data endpoint |
| Landing Page — Pricing section (all 5 plans) | Developer | 1 | Critical | Accurate plan details |
| Landing Page — Statistics bar + Why Indipips section | Developer | 0.5 | High | Hard-coded initially |
| Landing Page — FAQ section (10 questions) | Developer | 0.5 | High | Content finalized |
| Landing Page — Footer with all links | Developer | 0.5 | Medium | Legal pages linked |
| Create Terms & Conditions page (legal content) | Developer | 0.5 | Critical | Must exist before launch |
| Create Privacy Policy page (PDPB compliant) | Developer | 0.5 | Critical | Must exist before launch |
| Initialize Razorpay account + test API keys | Developer | 0.5 | Critical | Business account needed |
| Week 2 review — full landing page QA on mobile + desktop | Developer | 0.5 | High | Cross-browser test |

Week 2 Milestone: Full landing page live + all core backend APIs documented and tested via Postman

| W3 | WEEK 3 — Trader Dashboard + Payment Integration | Days 15–21 |
| --- | --- | --- |

### Objectives

- Build complete Trader Dashboard UI (all components)

- Complete Razorpay payment integration end-to-end

- Build challenge purchase flow from UI to DB

- Implement basic P&L display on dashboard

- Set up Socket.io for real-time communication foundation

| Task / Deliverable | Owner | Days | Priority | Dependency / Notes |
| --- | --- | --- | --- | --- |
| Build Trader Dashboard layout — sidebar + navbar + routing | Developer | 1 | Critical | React Router setup |
| Build Account Summary card component (balance, P&L, status) | Developer | 0.5 | Critical | Real-time data feed |
| Build P&L Chart component (Recharts line chart) | Developer | 1 | Critical | Historical + intraday |
| Build Drawdown Gauge component (circular meter) | Developer | 1 | Critical | Visual risk indicator |
| Build Daily Loss Monitor component (progress bar) | Developer | 0.5 | Critical | Color coded: green/amber/red |
| Build Rules Compliance Panel (checklist with status) | Developer | 0.5 | Critical | All 10 rules listed |
| Build Recent Trades Table (sortable, filterable) | Developer | 1 | High | Pagination required |
| Build Challenge Progress Widget (circular progress) | Developer | 0.5 | High | Profit target % |
| Build Challenge Timer component (days/hours remaining) | Developer | 0.5 | High | Countdown from expiry |
| Razorpay — Create order API + frontend checkout modal | Developer | 1 | Critical | Test mode first |
| Razorpay — Webhook handler for payment confirmation | Developer | 1 | Critical | Signature verification required |
| Razorpay — Auto-create challenge after payment success | Developer | 0.5 | Critical | Atomic transaction |
| Razorpay — GST invoice auto-generation | Developer | 0.5 | High | 18% GST calculation |
| Build Plan Selection + Checkout flow (multi-step) | Developer | 1 | Critical | UX must be seamless |
| Setup Socket.io server + client connection | Developer | 0.5 | Critical | Foundation for real-time |
| Week 3 review — complete payment flow test (Rs. 1 test) | Developer | 0.5 | Critical | End-to-end payment test |

Week 3 Milestone: Trader can register, pay, and see their dashboard — full challenge purchase flow working end-to-end

| W4 | WEEK 4 — Risk Engine + Broker API Integration | Days 22–28 |
| --- | --- | --- |

### Objectives

- Build the core Risk Management Engine (RME) — most critical component

- Integrate Upstox Paper Trading API for trade auto-sync

- Implement real-time P&L updates via Socket.io

- Implement automatic account suspension on rule breach

- Build Trades API and trade history storage

| Task / Deliverable | Owner | Days | Priority | Dependency / Notes |
| --- | --- | --- | --- | --- |
| Design Risk Engine architecture and event-driven flow | Developer | 1 | Critical | Refer SRS Section 13 |
| Build RME core service — rule evaluation logic | Developer | 2 | Critical | All 8 rules implemented |
| Implement Daily Loss Limit checker (real-time) | Developer | 1 | Critical | Resets at 9:15 AM IST |
| Implement Max Drawdown checker (peak balance tracking) | Developer | 1 | Critical | Permanent closure on breach |
| Implement Consistency Rule checker (40% single day cap) | Developer | 0.5 | High | End-of-day evaluation |
| Implement Profit Target achievement detection | Developer | 0.5 | Critical | Auto-pass trigger |
| Implement automatic account suspension service | Developer | 1 | Critical | Instant on breach |
| Upstox Paper Trade API — OAuth connection flow | Developer | 1 | Critical | Trader connects from dashboard |
| Upstox API — Real-time order webhook handler | Developer | 1 | Critical | Trade sync on execution |
| Upstox API — Positions and portfolio polling (5-sec fallback) | Developer | 0.5 | High | Fallback if webhook fails |
| Build Trade Storage service (save all trades to DB) | Developer | 0.5 | Critical | Full audit trail |
| Build P&L calculation service (realized + unrealized) | Developer | 1 | Critical | Accurate to paise |
| Socket.io — emit real-time events to trader dashboard | Developer | 0.5 | Critical | Dashboard live update |
| Socket.io — emit breach alert to trader (instant notification) | Developer | 0.5 | Critical | UI alert on rule breach |
| End-of-day automation (3:31 PM IST cron job) | Developer | 0.5 | Critical | node-cron daily evaluation |
| Week 4 review — simulate 10 trades, verify RME triggers correctly | Developer | 1 | Critical | Full RME integration test |

Week 4 Milestone: Risk Engine live — real trades syncing, drawdown tracked in real-time, automatic suspension working on rule breach

| W5 | WEEK 5 — Admin Panel + KYC + Payout System | Days 29–35 |
| --- | --- | --- |

### Objectives

- Build complete Admin Panel with all management features

- Integrate Aadhaar eKYC via UIDAI authorized provider

- Build Payout request and approval system

- Implement bank account verification

- Build notification system (email + SMS)

| Task / Deliverable | Owner | Days | Priority | Dependency / Notes |
| --- | --- | --- | --- | --- |
| Admin Panel — Layout, routing, and sidebar navigation | Developer | 0.5 | Critical | Separate admin subdomain |
| Admin Panel — Overview dashboard (KPI cards + charts) | Developer | 1 | Critical | Revenue, traders, challenges |
| Admin Panel — Traders management table (search, filter, sort) | Developer | 1 | Critical | Suspend/reinstate actions |
| Admin Panel — Active challenges monitor (real-time risk table) | Developer | 1 | Critical | Color-coded drawdown levels |
| Admin Panel — Payout queue (pending/approved/rejected tabs) | Developer | 1 | Critical | Approve/reject with notes |
| Admin Panel — Revenue analytics (charts via Recharts) | Developer | 0.5 | High | Daily/weekly/monthly view |
| Admin Panel — KYC verification queue | Developer | 0.5 | High | Manual review fallback |
| Admin Panel — Announcement/notification broadcast tool | Developer | 0.5 | Medium | Email all traders |
| Aadhaar KYC — Integrate UIDAI API provider (Digio/Signzy) | Developer | 1 | Critical | Test with sandbox first |
| Aadhaar KYC — OTP verification flow frontend + backend | Developer | 1 | Critical | Auto-populate name from Aadhaar |
| PAN card collection + validation (format check) | Developer | 0.5 | High | Required for payouts > Rs.50K |
| Bank account details form + IFSC validation API | Developer | 0.5 | High | Razorpay bank validation |
| Payout Request API (trader submits withdrawal) | Developer | 0.5 | Critical | Min amount validation |
| Payout Approval API (admin approves + initiates transfer) | Developer | 1 | Critical | Razorpay Payouts API |
| SendGrid — Setup all email templates (10 types) | Developer | 1 | High | Branded HTML templates |
| MSG91 — SMS templates for OTP + alerts + payouts | Developer | 0.5 | High | DLT registration needed |
| Week 5 review — test KYC flow + payout flow end-to-end | Developer | 0.5 | Critical | Full flow validation |

Week 5 Milestone: Admin can manage traders, approve payouts, view risk — KYC fully automated via Aadhaar

| W6 | WEEK 6 — Referral, Certificates, Leaderboard & Polish | Days 36–42 |
| --- | --- | --- |

### Objectives

- Build complete referral and affiliate program

- Build digital certificate generation system (PDF)

- Build public leaderboard

- Mobile responsiveness audit and fixes across all pages

- Performance optimization — lazy loading, caching, compression

| Task / Deliverable | Owner | Days | Priority | Dependency / Notes |
| --- | --- | --- | --- | --- |
| Referral code generation + tracking system | Developer | 0.5 | High | Auto-generated on registration |
| Referral earnings calculation (10% of referee fee) | Developer | 0.5 | High | Wallet credit system |
| Wallet balance system (accumulate + redeem credits) | Developer | 1 | High | Use wallet at checkout |
| Referral dashboard page (stats, earnings, leaderboard) | Developer | 0.5 | High | Visual referral stats |
| Affiliate program — application form + approval flow | Developer | 0.5 | Medium | Admin approves affiliates |
| Affiliate dashboard (clicks, conversions, earnings) | Developer | 0.5 | Medium | Separate affiliate portal |
| Digital Certificate PDF generation (pdfkit/puppeteer) | Developer | 1 | High | Branded certificate design |
| Certificate upload to AWS S3 + shareable URL | Developer | 0.5 | High | Public verification page |
| Certificate verification public page (verify by code) | Developer | 0.5 | High | Trust-building feature |
| Public leaderboard page (top 50 funded traders) | Developer | 0.5 | Medium | Opt-out option available |
| Leaderboard daily refresh cron job (midnight IST) | Developer | 0.5 | Medium | node-cron |
| Mobile responsiveness — full audit of all pages | Developer | 1 | Critical | Test on 320px to 1440px |
| Mobile responsiveness — fix all layout issues found | Developer | 1 | Critical | Tailwind responsive classes |
| Performance — implement Redis caching for plans, leaderboard | Developer | 0.5 | High | Reduce DB load |
| Performance — image compression + lazy loading | Developer | 0.5 | Medium | Core Web Vitals |
| SEO — meta tags, og:image, sitemap.xml, robots.txt | Developer | 0.5 | Medium | Google indexing |
| Week 6 review — share beta link with 3 test traders | Developer | 0.5 | High | First real user feedback |

Week 6 Milestone: Feature-complete platform — all modules built, mobile responsive, first beta users testing

| W7 | WEEK 7 — Integration Testing, Bug Fixes & Hardening | Days 43–49 |
| --- | --- | --- |

### Objectives

- End-to-end integration testing of all user journeys

- Fix all bugs found during testing

- Load testing — verify system handles 1,000 concurrent users

- Security hardening — pen testing, OWASP checks

- Final content review — all pages, emails, SMS templates

| Task / Deliverable | Owner | Days | Priority | Dependency / Notes |
| --- | --- | --- | --- | --- |
| Write E2E test cases for all 8 critical user journeys | Developer | 1 | Critical | Use Playwright or Cypress |
| E2E Test: Register → KYC → Purchase challenge → Dashboard | Developer | 0.5 | Critical | Happy path test |
| E2E Test: Trade sync → RME evaluation → pass challenge | Developer | 1 | Critical | Core business flow |
| E2E Test: Fail challenge → suspension → retry discount | Developer | 0.5 | Critical | Failure flow validation |
| E2E Test: Payout request → Admin approval → bank transfer | Developer | 0.5 | Critical | Financial flow test |
| E2E Test: Referral code → sign up → commission credited | Developer | 0.5 | High | Referral accuracy test |
| API stress test with k6 — simulate 100 concurrent users | Developer | 0.5 | High | Response time < 500ms |
| API stress test — simulate 1000 concurrent users | Developer | 0.5 | Critical | MVP capacity target |
| Database query optimization — add indexes on heavy queries | Developer | 1 | High | EXPLAIN ANALYZE queries |
| Security: Enable rate limiting on all endpoints | Developer | 0.5 | Critical | express-rate-limit |
| Security: SQL injection test (Prisma parameterized queries) | Developer | 0.5 | Critical | OWASP Top 10 check |
| Security: XSS test on all input fields | Developer | 0.5 | Critical | DOMPurify + CSP headers |
| Security: Verify all sensitive data is encrypted at rest | Developer | 0.5 | Critical | AES-256 audit |
| Security: Admin IP whitelist implementation | Developer | 0.5 | High | Cloudflare firewall rules |
| Review and finalize all email templates (10 templates) | Developer | 0.5 | High | Branding consistency |
| Review and finalize all SMS templates (5 templates) | Developer | 0.5 | High | DLT compliant content |
| Content audit — all pages for typos, accuracy, legal | Developer | 0.5 | High | Legal review of T&C |
| Week 7 review — fix all P0 and P1 bugs found | Developer | 1 | Critical | Zero critical bugs before launch |

Week 7 Milestone: Zero critical bugs — platform handles 1000 users, security hardened, all tests passing

| W8 | WEEK 8 — Production Deployment & Beta Launch | Days 50–60 |
| --- | --- | --- |

### Objectives

- Deploy all services to production environment

- Configure domain, SSL, CDN, monitoring

- Onboard first 20-50 beta traders

- Monitor system stability for 48 hours post-launch

- Prepare investor pitch with live platform demo

| Task / Deliverable | Owner | Days | Priority | Dependency / Notes |
| --- | --- | --- | --- | --- |
| Switch Razorpay from test mode to live mode | Developer | 0.5 | Critical | Business verification needed |
| Switch all APIs from sandbox to production (Aadhaar, MSG91) | Developer | 0.5 | Critical | Production API keys |
| Configure custom domain: indipips.com on Vercel | Developer | 0.5 | Critical | DNS propagation 24-48hrs |
| Configure admin.indipips.com subdomain | Developer | 0.5 | Critical | Separate admin access |
| Configure api.indipips.com subdomain for backend | Developer | 0.5 | Critical | CORS configured correctly |
| Setup Cloudflare WAF + DDoS protection | Developer | 0.5 | Critical | Free tier sufficient for MVP |
| Setup SSL certificates (auto via Cloudflare) | Developer | 0.5 | Critical | HTTPS enforced everywhere |
| Setup Sentry error monitoring (frontend + backend) | Developer | 0.5 | High | Real-time error alerts |
| Setup automated database backups (daily to S3) | Developer | 0.5 | Critical | Disaster recovery |
| Configure production environment variables | Developer | 0.5 | Critical | Never hardcode secrets |
| Final deployment — frontend to Vercel prod | Developer | 0.5 | Critical | Zero downtime deploy |
| Final deployment — backend to Railway prod | Developer | 0.5 | Critical | Health check endpoint live |
| Smoke test — verify all features on production | Developer | 1 | Critical | Complete end-to-end on prod |
| Onboard 5 internal beta testers (friends/family) | Developer | 1 | Critical | Real account creation test |
| Monitor system for 24 hours — check logs, Sentry, DB | Developer | 1 | Critical | Watch for errors |
| Announce beta launch on social media + trading communities | Business | 0.5 | High | Twitter/X, Telegram groups |
| Onboard first 20-50 traders via waitlist | Business | 1 | High | Offer early bird discount |
| Prepare live demo for investor pitch (screen recording) | Business | 1 | High | Show complete user journey |
| Day 60 — Final review + investor deck update with live stats | Business | 0.5 | High | Platform is now real proof! |

Week 8 Milestone: INDIPIPS IS LIVE — production platform deployed, first traders onboarded, investor demo ready!

# 3. Parallel Development Tracks

The following tracks run simultaneously throughout the 8 weeks. This is what makes 60-day delivery possible — nothing waits for anything else unless there is a hard dependency.

## 3.1 What Can Run in Parallel

| Track A (Backend) | Track B (Frontend) | Track C (Risk Engine) | Track D (Integrations) |
| --- | --- | --- | --- |
| Database schema design | Landing page HTML/CSS | RME architecture design | Razorpay account setup |
| Auth APIs (register, login) | Component library setup | Rule evaluation logic | Upstox API keys setup |
| Challenge CRUD APIs | Dashboard UI layout | Socket.io server setup | UIDAI API provider setup |
| Trades storage API | P&L chart component | Drawdown calculator | SendGrid templates |
| Payout APIs | Admin panel layout | Cron job setup | MSG91 DLT registration |
| Referral system APIs | Certificate UI page | Event emitter system | AWS S3 bucket setup |

## 3.2 Hard Dependencies (Must Complete In Order)

| # | Task | Depends On | Impact if Delayed |
| --- | --- | --- | --- |
| 1 | Any API development | Database schema complete | All backend blocked |
| 2 | Trader Dashboard data | Backend APIs complete | UI shows empty/mock data |
| 3 | Razorpay integration | Challenge Plans API ready | No payments possible |
| 4 | Risk Engine execution | Broker API integration done | No real trade monitoring |
| 5 | Payout system | KYC + Bank verification done | Cannot pay traders |
| 6 | Production deployment | All E2E tests passing | Risky live deployment |
| 7 | Beta user onboarding | Production deployed + smoke tested | Users face broken experience |

# 4. Pre-Development Setup Checklist

Complete ALL of these BEFORE writing a single line of code. This saves hours of mid-development blockers.

## 4.1 Accounts & Services to Register (Day 0)

| Service | Purpose | Cost | Time to Approve |
| --- | --- | --- | --- |
| GitHub Account | Code repository + version control | Free | Instant |
| Vercel Account | Frontend hosting | Free | Instant |
| Railway Account | Backend + DB hosting | Free (then ~Rs. 2K/mo) | Instant |
| Supabase Account | PostgreSQL managed hosting | Free | Instant |
| Razorpay Business Account | Payment gateway — INR | Free (2% per txn) | 2-3 business days |
| SendGrid Account | Transactional emails | Free (100/day) | Instant |
| MSG91 Account | SMS + OTP delivery | Pay per use | 1-2 days (DLT reg) |
| AWS Account | S3 for KYC docs + certificates | Pay per use (~Rs.500/mo) | Instant |
| Upstox Developer Account | Broker API for paper trading | Free | 1-2 days |
| UIDAI API Provider (Digio/Signzy) | Aadhaar eKYC integration | Rs. 5-10 per verification | 3-5 business days |
| Cloudflare Account | WAF + CDN + SSL + DNS | Free | Instant |
| Sentry Account | Error monitoring | Free tier | Instant |
| Domain: indipips.com | Website domain | ~Rs. 1,000/year | Instant (then DNS: 24-48hr) |

## 4.2 Development Environment Setup

- Node.js v20 LTS installed locally

- PostgreSQL 15 installed locally for development

- Redis installed locally (Docker recommended)

- VS Code with extensions: ESLint, Prettier, Prisma, GitLens

- Postman or Insomnia for API testing

- Git configured with SSH key for GitHub

- .env.local file created with all development keys

- README.md created with setup instructions

# 5. Risk Register & Contingency Plan

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Razorpay business account delayed (KYC) | Medium | High | Start Razorpay registration Day 1. Use test mode to build while waiting for approval. |
| UIDAI API provider onboarding delayed | High | Medium | Use manual KYC (document upload) as fallback for first 30 days. Replace with Aadhaar later. |
| Upstox API changes or downtime | Low | High | Also integrate Zerodha Kite API as backup. Paper trade mock engine for testing. |
| MSG91 DLT registration delayed | Medium | Medium | Use email-only OTP initially. DLT registration takes 3-5 days — start early. |
| Developer burnout or timeline slip | Medium | High | Built 2-day buffer into each week. Week 8 has 10 days instead of 7. |
| Security vulnerability found in audit | Medium | Critical | Week 7 dedicated to security. Fix all Critical/High issues before launch. |
| Database performance under load | Low | High | Add indexes in Week 7. Use Redis caching throughout. Monitor with pg_stat. |
| Broker API trade sync delays (>5 sec) | Medium | High | Implement 5-second polling fallback alongside webhooks. |

# 6. Launch Success Metrics

These are the KPIs to measure at the end of Day 60 to confirm a successful MVP launch:

| Metric | Target | How to Measure |
| --- | --- | --- |
| Platform uptime | 99.9% | Uptime monitoring via Railway + Cloudflare |
| Page load time (landing) | < 2 seconds | Google PageSpeed Insights |
| API response time (P95) | < 500ms | Railway logs + Sentry performance |
| Payment success rate | > 95% | Razorpay dashboard |
| Risk engine accuracy | 100% | Manual test: trigger each rule breach |
| KYC completion rate | > 80% | Admin panel analytics |
| Beta traders onboarded | 20-50 | Admin panel trader count |
| Zero P0 (critical) bugs | 0 bugs | Sentry error count |
| Mobile Lighthouse score | > 85 | Google Lighthouse audit |
| Investor demo ready | Yes | Recorded walkthrough + live demo |

# 7. Suggested Daily Development Schedule

As a college student building this solo, here is a recommended daily schedule to hit the 60-day target while managing college alongside:

| Time Slot | Activity | Hours |
| --- | --- | --- |
| 6:00 AM - 7:00 AM | Morning review — check yesterday's progress, plan today's tasks | 1 hr |
| 7:00 AM - 9:00 AM | Deep work — complex backend/algorithm coding (Risk Engine, APIs) | 2 hrs |
| College hours | College — attend classes | - |
| 4:00 PM - 5:00 PM | Review + small tasks — bug fixes, documentation, UI tweaks | 1 hr |
| 6:00 PM - 9:00 PM | Deep work — frontend components, integrations, testing | 3 hrs |
| 9:00 PM - 10:00 PM | End of day — commit code, update progress notes, plan tomorrow | 1 hr |
| Total Daily | Productive coding time | 7-8 hrs/day |
| Weekends | Catch-up + buffer days — tackle harder problems | 8-10 hrs/day |

Pro Tip: Use Claude as your AI pair programmer during every coding session. Don't Google — just ask Claude. This alone saves 2-3 hours per day and is what makes 60-day delivery realistic for a solo developer.

# 8. Post-Launch Roadmap (Day 61 Onwards)

| Month | Focus | Key Features |
| --- | --- | --- |
| Month 3 | Stability + Growth | Fix bugs from real users, social media marketing, reach 100 traders/month |
| Month 4 | Scale & Investment | Pitch investors with live platform + real revenue data, hire 1 backend dev |
| Month 5 | Feature Expansion | Zerodha integration, advanced analytics dashboard, trader community Discord |
| Month 6 | Mobile App | React Native app for iOS + Android, push notifications |
| Month 7-8 | Scale Infrastructure | Migrate to AWS ECS, add read replicas, support 5000+ concurrent traders |
| Month 9-10 | Product Expansion | Add educational courses, trading tools subscription, YouTube content |
| Month 12 | Market Leadership | 10,000+ traders, Rs. 1 Crore+ monthly revenue, Series A fundraise |

Day 1 starts the moment you open VS Code. Let's build Indipips.

Indipips Private Limited  |  Development Timeline v1.0  |  Confidential